## Information
INFORMATION SHEET
EDS 2022: DIABETES SERVICES & CHAPLAINCY SERVICES
REVIEW PERIOD: APRIL 2022 TO MARCH 2023
ORGANISATIONS | EDI LEADS | SERVICE LEADS DIABETES | SERVICE CHAPLAINCY | EDS BOARD CHAMPIONS | EDS RESPONSIBLE OFFICERS | HEAD OF PATIENT EXPEREINCE | KEY STAKEHOLDERS (Internal to NHS) | KEY STAKEHOLDERS (External) | DATA SOURCES
Northampton General Hospital | Matt Asbrey | 1 Jonathan Loasby 2 Pad Boovalingam | Lisa Cooper | Tracey Robson | Matt Asbrey | Chris Johnson | 1. Service Leads, 2. EDI Leads, 3. Chaplaincy, Trade Unions, 4. Carers Staff Network, 5. Health Inequalities Leads, 6. Patient Expereince Leads, 7. Complaints Teams, 8. Serious Incidents Teams, 9. Freedom to Speak Up Guardians. 10. Primary Care - to incude General Practice | 1 Service Users, 2 Patients, 3 Public, 4 Community Groups, 5 Faith Groups, 6 Northamptonshire Carers | NHS Secondary Uses Service (SUS) The General Practice Patient Survey National Cancer Patient Experience Survey CQC National Patient Surveys The Friends and Family Test (FFT) Serious Incidents Never Events Complaints as reported by NHS providers Accessible Information Standard (AIS) Reasonable adjustments as made by NHS organisations Health Inequalities Improvement Dashboard Local surveys and research JSNA Healthwatch (Healthwatch conduct surveys which will help with evidence being collected) WRES & WDES Reports Equal Pay Audits Gender Pay Gap Equality Impact Assessments of Services being reviewed
Kettering General Hospital |  | 1 Linda McGranahan 2 Dr Kish Patel | Neil Tyrer | Catherine Wills | Matt Asbrey | Pam Smith | As Above | As Above
Northamptonshire Healthcare NHS Foundation Trust | 1 David Ledger 2 Pauline Nyakatawa | 1 Lynsey Burgess 2 Tracey Dempster | 1 Odette Douglas 2 Sameen Malik | Chris Oakes | 1 David Ledger 2 Pauline Nyakatawa | Tendai Ngdongwe | As Above | As Above
Integrated Care Northamptonshire | Diana Belfon | n/a | n/a | Yvonne Higgins | Yvonne Higgins | n/a | As Above | As Above
Integrated Care Board | Satvinder Buttar |  |  | Yvonne Higgins | Yvonne Higgins |  | As Above | As Above

## Action Plan
ACTION PLAN |  |  |  | KEY
EDS 2022: DIABETES SERVICES & CHAPLAINCY SERVICES |  |  |  | Overdue
REVIEW PERIOD: APRIL 2022 TO MARCH 2023 |  |  |  | Ongoing
AUTHOR: DIANA BELFON, ICN EDI SPECIALIST |  |  |  | Completed
EDS 2022 DOMAIN 1 - CRITERIA | ACTIVITY | DETAILED ACTION | RESPONSIBLE PERSON | DEADLINE | RAG
1A: Service users have required levels of access to the service 1B: Individual service user’s health needs are met 1C: When service users use the service, they are free from harm 1D: Service users report positive experiences of the service | 1 Public notice for EDS2022 plans | Each organisation to publish a notice about the EDS2022 Plans on their websites. ICN EDI Specialist to communicate with Gaynor Walker from NHSE about the appropriate wording for the notice, and share with respective organisations accordingly. | ICN EDI Specialist, Service Leads and EDI Leads | 2023-01-01
| 2 Notification to organisations of ICB approach to EDS 2022 | Inform CEOS, COOs, EDS 2022 Board Champions and EDS 2022 Responsible Officers of the ICB approach to EDS 2022. | ICN EDI Specialist | 2023-01-01
| 3 Arrange an EDS2022 briefing meeting with EDI Leads and Service Leads | 1. ICN EDI Specialist to meet with EDI Leads and Service Leads to inform them of the EDS2022 plans. 2. Discuss data collection and collation. 3. Inform EDI Leads and Service Leads that Integrated Care Northamptonshire will be a 'test case' for NHS England, and will be working with Gaynor Walker from NHS England. | ICN EDI Specialist | early February 2023
| 4 Announcement of services to be reviewed and justification for reviewing services | 1 ICN EDI Specialist, Service Leads and EDI Leads to inform their respective organisation's governance systems, patient/service user groups, community groups and the public which services have been chosen for review. 2 Any key stakeholders identified in the 'Information' worksheet (within this Excel workbook) should also be informed about the services to be reviewed. | ICN EDI Specialist, Service Leads and EDI Leads | 2023-02-01
| 5 Request data (items 1A to 1D) from services being reviewed. | 1. Contact Service Leads and EDI Leads to request data. 2. Data collected should be by protected characteristics. 3. The Maternity & Pregnancy protected characteristics to include 'Paternity'. 4. Share possible data sources where information could be retrieved. 5. Ensure EDS 2022 Technical Guidance (Domain 1 Section) is shared with Service Leads and EDI Leads. | ICN EDI Specialist | 2023-03-01
| 6. Data collation by services | Check with services how data collation is progressing | ICN EDI Specialist | 2023-04-01
| 7 Services to submit data to ICN EDI Specialist and ICN Analyst | 1. Service Leads and EDI Leads to submit data to ICN EDI Specialist and ICN Anaylist for review. 2. Each organisation should ensure that evidence and conclusions are also available in 'Easy Read' format so that it is available for the Focus Groups that will conduct the scoring/rating exercise. | Service Leads: NHFT/NGH/KGH/ICB | 2023-05-01
| 8 Analysis of Service Data | ICN to analyse data from Service Leads and EDI Leads. | ICN Analyst ICN EDI Specialist | 2023-06-01
| 9 Focus Groups to be set up | ICN EDI Specialist to work with EDI Leads, Service Leads, Patient Experience Leads and Community Groups to set up a Focus Group to score Services against the criteria for EDS2022 Domain 1. | ICN EDI Specialist EDI Leads Service Leads Patient Experience Leads | 2023-07-01
| 10 Focus Group Scoring & Rating Training | ICN EDI Specialist to arrange a 'Scoring & Rating' training session for Focus Group members to equip them to conduct the EDS2022 scoring and rating of services under review. | ICN EDI Specialist | 2023-07-01
| 11 Focus Groups to conduct Scoring & Rating | ICN EDI Specialist to coordinate a series of Focus Groups to score and rate services under review. | ICN EDI Specialist | 2023-09-01
| 12 Service Improvement Plans to be developed | ICN EDI Specialist and EDI Leads to work with Service Leads to develop Service Improvement Plans. | ICN EDI Specialist EDI Leads Service Leads | 2023-10-01
| 13 Service Improvement Plans presented to Boards & Governance Processes for approval | Following completion of the scoring and rating by the Focus Groups, the ICN EDI Specialist, Service Leads and EDI Leads to present Service Improvement Plans to the ICN People Board, Integrated Care Board, identified 'System Boards' egg Diabetes Board, and organisational governance processes. | ICN EDI Specialist EDI Leads Service Leads | November/December 2023
| 14 Service Improvement Plans to be shared with Focus Groups | Service Improvement Plans to be shared with members of the focus groups that conducted the scoring and rating exercise. | ICN EDI specialist | 2024-01-01
| 15 Publication of Service Improvement Plans | 1. Service Improvement Plans to be published via the 1. Annual Equality Information Report for each organisation. 2. Shared with local councils and NHS organisations. 3. Published on the ICN website and the website of each participating NHS organisation. | ICN EDI Specialist EDI Leads Service Leads | 2024-01-01
| 16 Accountability & Governance | 1. ICN EDI Specialist, Service Leads and EDI Leads to link Service Improvement Plans to Equality Objectives | ICN EDI Specialist EDI Leads Service Leads | 2024-01-01
|  | 2. ICN EDI Specialist to set up 3 x meetings to monitor Service Improvement Plans. ICN EDI Specialist, Service Leads and EDI Leads to update respective boards/committees accordingly. Also at these meetings, the ICN EDI Specialist to obtain an update from Service Leads and EDI Leads of organisational improvement plans for EDS 2022 Domain 2 (Workforce Health & Wellbeing) and Domain 3 (Inclusive Leadership). | ICN EDI Specialist EDI Leads Service Leads | January, March, June 2024
|  | 3. ICN EDI Specialist, Service Leads, EDI Leads to present quarterly updates on the progress of service plans to their own various boards. | ICN EDI Specialist EDI Leads Service Leads | January, March, June 2024