Equality & Diversity Staff Group

Equality Objectives Four Year Plan 2016 – 2020 (Updated February 2018)

March 2020 Progress Report

| Equality Delivery System Goal | Objective | Key Actions | Detailed Actions | Lead | Timescales | Completed / Ongoing / To do | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Representative and supported workforce The NHS is asked to…… The NHS should increase the diversity and quality of the working lives of the paid and unpaid workforce supporting all staff to better respond to patients’ and communities’ needs. | We will improve our staff satisfaction rates as reported in the annual staff survey. We will make year on year improvements on our staff survey results, aiming to achieve top 20% of acute Trusts for staff engagement. We will improve the experiences and treatment between White staff and BME staff at the Trust by progressing WRES and monitoring outcomes. | On receipt of the annual Staff Survey results carry out gap analysis and take appropriate action in relation to the key findings that relate to the workforce. | Analyse the reports provided to identify: If and where the results have improved and share the results (concerns and improvements) with appropriate managers. If the Trust is in the top 20% of acute Trusts for staff engagement. Areas of concern and improvements for the specific questions relating to Equality & Diversity and the protected characteristics and share these with the Equality & Diversity Staff Group. | Head of OD Head of OD DD of HR | March 2016 | Completed | 2019 Staff Survey closed on 29 November 2019. Analysis and dissemination commenced in February 2020. |
|  |  |  |  |  | March 2017 | Completed |  |
|  |  |  |  |  | March 2018 | Completed |  |
|  |  |  |  |  | March 2019 | Completed |  |
|  |  |  |  |  | March 2020 | Commenced |  |
|  |  |  | Develop a Respect and Support Campaign (a programmed series of materials) to help staff and colleagues recognise, address and report potential harassment and bullying. Session to also include age awareness and bullying and harassment. | Head of OD | Commenced March 2017 | Completed | The campaign was launched in June 2018, along with the Respect and Support Behavioural Framework - a document that sets out examples of expected behaviours from all staff. Training on the behaviours of staff and managers has commenced along with resilience training. |
|  |  |  | Review the two separate HR presentations (E&D and harassment & bullying) at Trust induction to combine into one session. | DD of HR | June 2018 | Completed | Review completed and as from June 2018 inductions the new HR presentation will commence. |
|  |  | On completion of the annual Workforce Race Equality Standard (WRES) baseline data exercise carry out a gap analysis against the previous year’s data and take appropriate action in relation to the indicators for the experiences and treatment between White staff and BME staff and continue to monitor these. | Analyse the data to identify areas of concern and improvements for the specific questions relating to Equality & Diversity and the protected characteristics and share these with the Equality & Diversity Staff Group, Workforce Committee and the Trust Board. | DD of HR | September 2016 | Completed | The analysis of the 2018/19 data took place in June/July 2019 and has been submitted to NHS England. The data was published on the NGH website in September 2019 |
|  |  |  |  |  | September 2017 | Completed |  |
|  |  |  |  |  | September 2018 | Completed |  |
|  |  |  |  |  | September 2019 | Completed |  |
|  |  |  |  |  | September 2020 | To Do |  |
|  |  |  | Carry out an audit on the recruitment and shortlisting processes to previous senior posts to identify what actions are required. | DD of HR | June 2016 | Completed |  |
|  |  |  | Provide recruitment training for managers which include a session on equality awareness. | Head of R & ES | Implement as from 2016 | Completed |  |
|  |  |  | Monitor and report on non-mandatory and CPD training by ethnicity. | DD of HR | August 2017 | Completed |  |
|  |  |  | Carry out a gap analysis of Trust equality and diversity activity against NHS Employers Equality & Diversity in Practice Top Ten Tips. | DD of HR | June 2016 | Completed |  |
|  |  | On completion of the annual Workforce Disability Equality Standard (WDES) baseline data exercise carry out a gap analysis against the previous year’s data and take appropriate action in relation to the indicators for the experiences and treatment between Disabled staff and Non-Disabled staff and continue to monitor these. | Analyse the data to identify areas of concern and improvements for the specific questions relating to Equality & Diversity and the protected characteristics and share these with the Equality & Diversity Staff Group, Workforce Committee and the Trust Board. | DD of HR | September 2019 | To Do | 2018/19 WDES data exercise commenced July 2019 and the data was published on the NGH website in September 2019 |
|  |  |  |  |  | September 2020 | To Do |  |
|  |  | On an annual basis carry out the Gender Pay Gap reporting process as required by the Equality Act 2010 (Gender Pay Gap Information) Regulations 2017 | Analyse the data to identify areas of concern and improvements for the and share these with the Equality & Diversity Staff Group, Workforce Committee and the Trust Board | Deputy Director of HR | March 2018 | Completed | Analysis for the 2019/20 data and the findings has been completed and shared with the Workforce Committee. The data was published on the Trust website and submitted to Gov.UK in February 2020. |
|  |  |  |  |  | March 2019 | Completed |  |
|  |  |  |  |  | March 2020 | Completed |  |
|  |  | Each Division to set and be accountable for their own equality and diversity objectives through the clinically led structure with divisional links to the Equality and Diversity Staff Group. | Each Division to be provided with Equality and Diversity data for their areas and with the support of their HR Business Partner analyse the data to identify if there are any areas for improvement/objectives that can be set. Each Division to also have a nominated lead to represent them at the Trust’s Equality and Diversity Staff Group. | DD of HR | September 2016 | Completed |  |
|  |  | Implement the staff engagement strategy centred on the Trust’s vision and values and the desired behaviours and performance of staff. | Organisational Development Team to lead on staff engagement, culture, communication and behaviours. | Head of OD | Commenced 2015 | Completed |  |
|  |  | Become a health promoting Trust that makes an active contribution to promoting and improving the wider health and wellbeing of our staff. | Implement the health and wellbeing strategy with the aim of improving the mental and physical health of employees and to help to reduce inequalities. | Health & Wellbeing Co-ordinator | Launched April 2016 | Completed |  |
|  |  | Work towards becoming a Disability Confident Leader | Review the criteria of the Disability Confident Leader Scheme (Level 3) to identify gaps and assess what actions are required | Head of HRSC | Commenced October 2018 | In progress | The Head of the HR Service Centre reviewed the criteria and presented a gap analysis to the E&DSG in December 2018. Comments and feedback were collated and will be circulated for final comments in December 2019. |
|  |  | Work towards achieving outstanding in relation to the CQC KLOE for E&D | Review the CQC Key Lines of Enquiry that relate to Equality and Diversity to identify gaps and assess what actions are required | DD of HR | Commenced December 2018 | Completed | The DD of HR reviewed the criteria and produced a gap analysis which has been circulated to the E&DSG for comments. Findings presented to the E&DSG in March 2019. |
|  |  | To be an inclusive employer who recognises and values difference, by demonstrating practices that recognise, respect, value and harness differences for the benefits for our staff | Commence working with Diversity by Design to run and conduct analysis of focus groups for staff on the protected characteristics | Head of OD | Commenced March 2019 | In progress | Workshops held on 27 March 2019. Report received for analysis. |
|  |  |  | To work with Diversity by Design and pilot alternative recruitment techniques to work towards removing unconscious bias during recruitment/interviews of applicants. | Director of W & T | Commenced March 2019 | In progress | Two roles have been selected for the pilot. |
|  |  |  | To investigate setting up a workforce BAME group | DD of HR | Commenced March 2019 | Completed | First meeting took place in July 2019 and schedule of dates for remained of 2019 and early 2020 have been planned. |

| Equality Delivery System Goal | Objective | Key Actions | Detailed Actions | Lead | Timescales | Completed / Ongoing / To do | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Inclusive leadership The NHS is asked to…… NHS organisations should ensure that equality is everyone’s business and everyone is expected to take an active part, supported by the work of specialist equality leaders and champions | We will improve our leadership and management capability. | Develop and deliver Leadership and Management programmes including equality & diversity and bullying & harassment | Commence Francis Crick for senior leaders | Head of OD | Commenced 2016 | Completed |  |
|  |  |  | Develop and commence leadership management training aimed at those who are new to leadership/management or existing leaders/managers that need to upskill | Head of OD | March 2018 | Completed |  |
|  |  |  | Develop and commence leadership management training aimed at those who are in a supervisory role who need to develop and learn practical and helpful skills to lead and manage their teams effectively | Head of OD | March 2018 | Completed |  |
|  |  |  | As part of the Leadership & Management training develop an equality and diversity module. | Head of OD | Commenced August 2019 | Ongoing | OD to review the training and include information on equality & diversity including specific reference to unconscious bias. |
|  |  | On completion of the annual Workforce Race Equality Standard (WRES) baseline data exercise carry out a gap analysis against the previous year’s data and take appropriate action in relation to the indicators that relate to leadership and continue to monitor these | Actively encourage all candidates including those from BME backgrounds to apply for very senior management roles - as and when vacancies arise through open and transparent recruitment and selection processes including values based recruitment. | Head of R & ES | September 2016 | Completed |  |
|  |  |  | Actively encourage all staff including those from BME backgrounds to apply for the Leadership and Development programmes through open and transparent publicity and application process. | Head of OD | January 2018 | Completed |  |