## Sheet1
Performance in Initiating Clinical Research
1st October 2016 - 30th September 2017
System generated field Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Patient Recruited? | Date of First Patient Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Patient Recruited | Duration between Date Site Selected and First Patient Recruited | Benchmark Met | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
106773 | 14/NE/1180 | 145170 | UKGRIS Risk Score Intervention Study | No |  |  |  |  | Within 70 Days | 2017-07-24 | 2017-07-24 | 2017-01-06
106774 |  | 226131 | A cross-sectional study to assess compliance with national recommendations for brand name prescribing of biological medicines in secondary care in the UK | Yes | 2017-10-16 | 21 | 25 | 46 | Yes |  | 2017-08-31 |  |  | 2017-09-21 |  | 2017-09-21
106775 | 17/NE/0200 | 220486 | SMART Registry_Boston Scientific_(0393-0026) | No |  |  |  |  | Within 70 Days | 2017-05-24 | 2017-08-10 | 2017-08-24 |  |  |  |  | D - Sponsor Delays | Contract negotiations | Sponsor
106776 | 17/EM/0005 | 215706 | CARD 4983 GALACTIC-HF | Yes | 2017-09-28 | 21 | 203 | 224 | No | 2016-12-19 | 2017-02-16 | 2017-02-15 | 2017-02-24 | 2017-03-09 |  | 2017-05-02 | F - No patients seen | No suitable patients seen | Neither
106777 | 16/SC/0462 | 208830 | DRAFFT 2 - Distal Radius Acute Fracture Fixation Trial 2 | Yes | 2017-04-11 | 89 | 52 | 141 | No | 2016-10-25 | 2016-11-21 | 2016-11-11 | 2017-03-09 | 2017-02-18 |  | 2017-03-03 | J - Other | Delay was due to staff training issues (GCP) | NHS Provider
106778 | 15/SW/0194 | 185459 | A randomized, double-blind, placebo-controlled, parallel-group, multicenter, event-driven phase 3 study to investigate the efficacy of finerenone on the progression of deterioration of kidney function in patients with type 2 diabetes mellitus and the clinical diagnosis of advanced diabetic kidney disease in addition to standard of care. | No |  |  |  |  | Within 70 Days | 2017-08-29 | 2017-09-11 | 2016-06-17
106779 | 15/SC/0448 | 183584 | A randomized, double-blind, placebo-controlled, parallel-group, multicenter, event-driven phase 3 study to investigate the efficacy of finerenone on the reduction of cardiovascular morbidity and mortality in patients with type 2 diabetes mellitus and the clinical diagnosis of early diabetic kidney disease in addition to standard of care | No |  |  |  |  | Within 70 Days | 2017-08-29 | 2017-09-11 | 2016-05-16
106780 | 17/NS/0018 | 223787 | Female Urgency, Trial of Urodynamics as Routine Evaluation (FUTURE study); a superiority randomised clinical trial to evaluate the effectiveness and cost effectiveness of invasive urodynamic investigations in management of women with refractory overactive bladder symptoms | No |  |  |  |  | Within 70 Days | 2017-09-21 | 2017-09-21 | 2017-08-11