## Sheet1
Performance in Initiating Clinical Research
1st January 2017 - 31st December 2017
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Patient Recruited? | Date of First Patient Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Patient Recruited | Duration between Date Site Selected and First Patient Recruited | Benchmark Met | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
113291 | 14/NE/1180 | 145170 | UKGRIS Risk Score Intervention Study | No |  | 134 |  |  | No | 2017-07-24 | 2017-07-24 | 2017-01-06 | 2017-11-10 | 2017-12-05 | Please Select... |  | D - Sponsor Delays | No green light given | Sponsor
113292 |  | 226131 | A cross-sectional study to assess compliance with national recommendations for brand name prescribing of biological medicines in secondary care in the UK | Yes | 2017-10-16 | 21 | 25 | 46 | Yes |  | 2017-08-31 |  |  | 2017-09-21 | Please Select... | 2017-09-21 |  | Exempt from REC review hence no REC number. Shown as an Interventional Study on Edge. | Please Select...
113293 | 17/NE/0200 | 220486 | SMART Registry_Boston Scientific_(0393-0026) | Yes | 2017-12-19 |  |  | 131 | No | 2017-05-24 | 2017-08-10 | 2017-08-24 | 2017-10-25 |  | Please Select... |  | D - Sponsor Delays | Contract negotiations | Sponsor
113294 | 17/EM/0005 | 215706 | CARD 4983 GALACTIC-HF | Yes | 2017-09-28 | 21 | 203 | 224 | No | 2016-12-19 | 2017-02-16 | 2017-02-15 | 2017-02-24 | 2017-03-09 | Please Select... | 2017-05-02 | F - No patients seen | No suitable patients seen | Neither
113295 | 15/SW/0194 | 185459 | A randomized, double-blind, placebo-controlled, parallel-group, multicenter, event-driven phase 3 study to investigate the efficacy of finerenone on the progression of deterioration of kidney function in patients with type 2 diabetes mellitus and the clinical diagnosis of advanced diabetic kidney disease in addition to standard of care. | Yes | 2018-01-16 | 74 | 35 | 109 | No | 2017-09-11 | 2017-09-29 | 2016-06-17 | 2017-12-05 | 2017-12-12 | Please Select... | 2017-12-18 | H - Contracting delays | Issues with sponsor accepting signature on contract | Sponsor
113296 | 15/SC/0448 | 183584 | A randomized, double-blind, placebo-controlled, parallel-group, multicenter, event-driven phase 3 study to investigate the efficacy of finerenone on the reduction of cardiovascular morbidity and mortality in patients with type 2 diabetes mellitus and the clinical diagnosis of early diabetic kidney disease in addition to standard of care | Yes | 2018-01-23 | 74 | 42 | 116 | No | 2017-09-11 | 2017-09-29 | 2015-08-26 | 2017-12-12 | 2017-12-12 | Please Select... | 2017-12-18 | H - Contracting delays | Issues with sponsor accepting signature on contract | Sponsor
113297 | 17/NS/0018 | 223787 | Female Urgency, Trial of Urodynamics as Routine Evaluation (FUTURE study); a superiority randomised clinical trial to evaluate the effectiveness and cost effectiveness of invasive urodynamic investigations in management of women with refractory overactive bladder symptoms | No |  | 85 |  |  | No | 2017-09-21 | 2017-09-21 | 2017-10-01 | 2017-12-04 | 2017-12-15 | Please Select... |  | D - Sponsor Delays | No green light from sponsor | Sponsor
114310 | 17/LO/1802 | 199038 | EQUIPTT (Evaluation of QUIPP app for Triage and Transfer) | No |  | 20 |  |  | Within 70 Days | 2017-12-01 | 2017-12-01 | 2017-11-23 | 2017-12-01 | 2017-12-21 | Please Select... |  |  | All sites will commence in Feb | Please Select...