## Sheet1
Performance in Initiating Clinical Research
1st January 2013 - 31st December 2018
ID | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
131434 | 17/YH/0393 | 234355 | PUGS (Paediatric Use of the AbbottSensorBasedGlucoseMonitoringSystem) | Yes | 2018-02-16 | 39 | 4 | 43 | 2018-01-04 | 2018-01-04 | 2018-02-07 | 2018-02-05 | 2018-02-12 | Please Select... | 2018-01-25 |  | First global patient | Please Select..
131435 | 18/LO/0116 | 239646 | Prexasertib in Recurrent Ovarian Cancer (JTJN) | Yes | 2018-04-12 | 62 | 21 | 83 | 2018-01-19 | 2018-01-19 | 2018-03-26 | 2018-03-19 | 2018-03-22 | Please Select... | 2018-04-10 | A - Permissions delayed/denied | Regulatory approvals not in place - national issue | Neither
134434 | 18/LO/0141 | 233922 | OPINION - A Phase IIIb, Single-arm, Open-label Multicentre Study of Olaparib Maintenance Monotherapy in Platinum Sensitive Relapsed non- Germline BRCA Mutated Ovarian Cancer Patients who are in Complete or Partial Response Following Platinum based Chemotherapy | Yes | 2019-01-08 | 116 | 88 | 204 | 2018-06-18 | 2018-06-18 | 2018-03-16 | 2018-09-27 | 2018-10-12 | Please Select... | 2018-10-19 | E - Staff availability issues | Significant capacity issues in R&D | NHS Provider
134638 | 18/SC/0222 | 223737 | NeoCLEAR: Neonatal Champagne Lumbar punctures Every time – An RCT. A multicentre, randomised controlled 2x2 factorial trial to investigate techniques to increase lumbar puncture success | Yes | 2018-09-29 | 90 | 12 | 102 | 2018-05-21 | 2018-06-19 | 2018-06-12 | 2018-09-14 | 2018-09-17 | Please Select... | 2018-09-19 |  |  | Please Select...