## Sheet1
Performance in Initiating Clinical Research
1st April 2017 - 30th March 2018
System generated field Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Patient Recruited? | Date of First Patient Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Patient Recruited | Duration between Date Site Selected and First Patient Recruited | Benchmark Met | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
117582 | 14/NE/1180 | 145170 | UKGRIS Risk Score Intervention Study | Yes | 2018-02-06 | 134 | 63 | 197 | No | 2017-07-24 | 2017-07-24 | 2017-01-06 | 2017-11-10 | 2017-12-05 | Please Select... | 2018-01-16 | D - Sponsor Delays | No green light given | Sponsor
117583 |  | 226131 | A cross-sectional study to assess compliance with national recommendations for brand name prescribing of biological medicines in secondary care in the UK | Yes | 2017-11-16 | 21 | 56 | 77 | No | 2017-08-08 | 2017-08-31 | 2017-05-30 | 2017-08-31 | 2017-09-21 | Please Select... | 2017-09-21 | J - Other | Exempt from REC review hence no REC number. Shown as an Interventional Study on Edge. | Neither
117584 | 17/NE/0200 | 220486 | SMART Registry_Boston Scientific_(0393-0026) | Yes | 2017-12-19 | 64 | 41 | 105 | No | 2017-09-05 | 2017-09-05 | 2017-08-24 | 2017-10-25 | 2017-11-08 | Please Select... |  | D - Sponsor Delays | Sponsor delays. Contract negotiations. Contract received on 30/10/2017. | Sponsor
117585 | 15/SW/0194 | 185459 | A randomized, double-blind, placebo-controlled, parallel-group, multicenter, event-driven phase 3 study to investigate the efficacy of finerenone on the progression of deterioration of kidney function in patients with type 2 diabetes mellitus and the clinical diagnosis of advanced diabetic kidney disease in addition to standard of care. | Yes | 2018-01-29 | 74 | 48 | 122 | No | 2017-09-11 | 2017-09-29 | 2016-06-17 | 2017-12-05 | 2017-12-12 | Please Select... | 2017-12-18 | H - Contracting delays | Issues with sponsor accepting signature on contract | Sponsor
117586 | 15/SC/0448 | 183584 | A randomized, double-blind, placebo-controlled, parallel-group, multicenter, event-driven phase 3 study to investigate the efficacy of finerenone on the reduction of cardiovascular morbidity and mortality in patients with type 2 diabetes mellitus and the clinical diagnosis of early diabetic kidney disease in addition to standard of care | Yes | 2018-02-06 | 74 | 56 | 130 | No | 2017-09-10 | 2017-09-29 | 2015-08-26 | 2017-12-08 | 2017-12-12 | Please Select... | 2017-12-18 | H - Contracting delays | Issues with sponsor accepting signature on contract | Sponsor
117587 | 17/NS/0018 | 223787 | Female Urgency, Trial of Urodynamics as Routine Evaluation (FUTURE study); a superiority randomised clinical trial to evaluate the effectiveness and cost effectiveness of invasive urodynamic investigations in management of women with refractory overactive bladder symptoms | No |  | 85 |  |  | No | 2017-09-21 | 2017-09-21 | 2017-10-01 | 2017-12-04 | 2017-12-15 | Please Select... | 2018-01-16 | D - Sponsor Delays | Delay on green light from sponsor | Sponsor
117588 | 17/LO/1802 | 199038 | EQUIPTT (Evaluation of QUIPP app for Triage and Transfer) | Yes | 2018-02-22 | 19 | 64 | 83 | No | 2017-12-01 | 2017-12-01 | 2017-11-23 | 2017-12-01 | 2017-12-20 | Please Select... | 2017-12-20 | J - Other | Due to the nature of the EQUIPTT study, which involves a 6 week pre-intervention data collection period, it is not possible to recruit to time and target | Neither
117589 | 17/YH/0393 | 234355 | PUGS (Paediatric Use of the AbbottSensorBasedGlucoseMonitoringSystem) | Yes | 2018-02-16 | 39 | 4 | 43 | Yes | 2018-01-04 | 2018-01-04 | 2018-02-07 | 2018-02-05 | 2018-02-12 | Please Select... | 2018-01-25 |  | First global patient | Please Select...
119034 | 18/LO/0116 | 239646 | Prexasertib in Recurrent Ovarian Cancer (JTJN) | Yes | 2018-04-12 | 62 | 21 | 83 | No | 2018-01-19 | 2018-01-19 | 2018-03-26 | 2018-03-19 | 2018-03-22 | Please Select... | 2018-04-10 | J - Other | Regulatory approvals not in place - national issue | Neither
119035 | 15/NE/0104 | 164257 | MYOPROSP | Yes | 2018-04-03 | 36 | 102 | 138 | No | 2017-10-11 | 2017-11-16 | 2016-05-19 | 2017-12-22 | 2017-12-22 | Please Select... | 2018-03-06 | D - Sponsor Delays | Site Initiation Visit delayed by sponsor due to lots of sites coming onboard | Sponsor